Livepeer Docs v2 — Developers Section

PLAN 3: Overall Updated Implementation Plan

Integrates quick fixes (Plan 1), content overhauls (Plan 2), and the Semantic Rollout batch structure. Provides the full ordered execution sequence.

March 2026  |  Aligned to SemanticUI-PLAN batches B16–B19  |  Platforms tab removed

# Key Architecture Decision — Platforms Tab Removed

DECISION (confirmed March 2026): The top-level Platforms tab has been removed from the docs navigation. As a result, developer-platforms/ remains permanently within the Developers section as the canonical home for Daydream, Livepeer Studio, Frameworks, Streamplace, and Embody product documentation. No redirect to /v2/platforms/* should be added. The builder-hub.mdx landing must be production-ready. See Plan 2 C01 for rewrite.

# Guiding Principles

Four principles govern all work in this section — non-negotiable:

- Accuracy first. Every code example, URL, and API claim must be verifiable against the GitHub repo, official APIs, or confirmed community sources. When in doubt, remove rather than guess.

- Gateway persona completeness. A developer who lands on any page must have a clear path to: (a) their first working call, (b) the next step, and (c) the full progression story. No dead ends.

- No dilution. The migration guardrails from SemanticUI-PLAN.md apply. Path fixes are path fixes. Content changes are content changes. They do not mix in the same commit.

- The Local SDK story is non-negotiable. The livepeer-python-gateway / local gateway SDK is the primary programmatic interface for developers. It must be documented with working code before the section is considered production-ready.

# Updated IA — Developers Section Post-Fix State

| Path | Section | Target Status | Batch |
| --- | --- | --- | --- |
| developer-portal.mdx | Portal landing | ✅ Clean after F01, F09, F14 | B16 |
| developer-platforms/ | Platforms Home (NEW ROLE — tab removed) | Rewrite per Plan 2 C01 | B19 |
| building-on-livepeer/ | Developer Guides | Add: authentication, access-the-network, local-gateway-sdk, fix quickstarts | B16 |
| ai-inference-on-livepeer/ai-pipelines/ | AI Pipelines (canonical) | ✅ Production-ready — BYOC, ComfyStream, Overview complete | B17 |
| ai-inference-on-livepeer/livepeer-ai/ | AI Supplementary | Clean stubs per F08; realtime-ai.mdx to be completed | B17 |
| livepeer-real-time-video/ | Video Streaming | Full rewrite per Plan 2 C07 | B16 |
| technical-references/ | APIs & SDKs | Update per Plan 2 C08 — SDK disambiguation critical | B18 |
| developer-tools/ | Tools & Dashboards | Clean gateways.mdx (F10); verify others | B18 |
| builder-opportunities/ | Grants, RFPs, OSS | Complete OSS contributions page | B19 |
| guides-and-resources/ | Guides | Add studio-migration.mdx (C09); verify contribution-guide | B18 |
| moved-to-about-livepeer-protocol/ | (REMOVE) | Redirects per F05 — remove from nav | B16 (prereq) |

# Execution Sequence

This sequence is ordered. Do not begin a phase until all items in the previous phase gate-pass.

## Phase 0 — Pre-Conditions (Before Any Developer Section Work)

These are requirements from SemanticUI-PLAN B00a/B00b that must be in place:

| Item | Requirement | Gate |
| --- | --- | --- |
| B00a | Lock semantic contract in docs governance. Add semantic-exceptions.json. Patch changed-file gates to include v2/developers/ paths. | node tests/unit/docs-navigation.test.js --strict-missing |
| B00b | Full route normalization — all v2/pages/** references updated to modern routes. docs.json pages/redirects normalized. | node tests/integration/v2-link-audit.js --full --strict |
| B00b | Developer section: ensure NO redirects pointing to /v2/platforms/* from /v2/developers/developer-platforms/* | Manual verify: grep docs.json for platforms redirect |

## Phase 1 — Quick Fixes (Plan 1, all F01–F15)

Execute all 15 fixes from Plan 1 as a single batch (B16 pre-work). Non-Negotiable Migration Guardrails apply — fix scope only, no content changes.

| Order | Fix | Guard |
| --- | --- | --- |
| 1st | F05 — Remove moved-to-about nav group + redirects | Must complete before any nav work |
| 2nd | F06 — Confirm no Platforms redirect in docs.json | Must confirm before Phase 2 C01 starts |
| 3rd | F01, F02, F03, F04, F09, F14, F15 — Portal and developer-guide fixes | Can run in parallel |
| 4th | F07, F08 — Duplicate AI stubs removal and livepeer-ai/ cleanup | After F03/F04 complete |
| 5th | F10, F11, F12, F13 — Tool pages, partners, stub deletion | Can run in parallel |
| Gate | node tests/run-pr-checks.js --base-ref docs-v2 | All 15 fixes must pass before Phase 2 |

## Phase 2 — Content Implementation (Plan 2, by Semantic Batch)

Execute content items in this order. Each item aligns to a SemanticUI batch. Complete semantic metadata (frontmatter contract) for each page as part of writing.

### B16 — Developer Root + Building On + Video Streaming

| Content Item | File | From Plan 2 | Dependencies |
| --- | --- | --- | --- |
| C03 | building-on-livepeer/access-the-network.mdx (NEW) | C03 | Phase 1 complete |
| C02 | building-on-livepeer/authentication.mdx (NEW) | C02 | access-the-network.mdx |
| C06 | building-on-livepeer/local-gateway-sdk.mdx (NEW) | C06 | authentication.mdx |
| C04 | building-on-livepeer/quick-starts/livepeer-ai.mdx (REWRITE) | C04 | authentication.mdx |
| C05 | building-on-livepeer/quick-starts/video-streaming.mdx (REWRITE) | C05 | authentication.mdx |
| C07 | livepeer-real-time-video/ section (REWRITE README + create 4 pages) | C07 | Quickstarts complete |
| C10 | building-on-livepeer/developer-guide.mdx (rebuild) | C10 | All above complete |

B16 Gate: node tests/integration/v2-link-audit.js --files <b16-files> --strict

### B17 — AI Pipelines + AI Inference

| Content Item | File | From Plan 2 | Dependencies |
| --- | --- | --- | --- |
| — | ai-pipelines/ (BYOC, ComfyStream, Overview) — already production-ready | — | Verify frontmatter contract only |
| — | livepeer-ai/realtime-ai.mdx — complete or redirect | F08 | F08 complete |
| — | Semantic frontmatter on all ai-inference pages | B17 contract | B16 gate passed |

B17 Gate: node tests/run-all.js --skip-browser

### B18 — Developer Tools + Guides + Technical References

| Content Item | File | From Plan 2 | Dependencies |
| --- | --- | --- | --- |
| C08 | technical-references/apis.mdx + sdks.mdx (UPDATE) | C08 | B16 complete |
| C09 | guides-and-resources/studio-migration.mdx (NEW) | C09 | sdks.mdx updated |
| — | developer-tools/ pages — verify completeness, fix F10/F11 | F10/F11 | Phase 1 |
| — | guides-and-resources/contribution-guide.mdx — complete | — | New content |

B18 Gate: node tests/integration/v2-link-audit.js --full --strict

### B19 — Developer Platforms + Builder Opportunities + Technical Refs

| Content Item | File | From Plan 2 | Dependencies |
| --- | --- | --- | --- |
| C01 | developer-platforms/builder-hub.mdx (REWRITE — Platforms tab removed) | C01 | B18 complete |
| C01 | developer-platforms/daydream/daydream.mdx (minimum viable) | C01 | builder-hub.mdx |
| C01 | developer-platforms/livepeer-studio/livepeer-studio.mdx (minimum viable) | C01 | builder-hub.mdx |
| C01 | developer-platforms/frameworks/frameworks.mdx (minimum viable) | C01 | builder-hub.mdx |
| C01 | developer-platforms/streamplace/*.mdx (minimum viable overview) | C01 | builder-hub.mdx |
| — | builder-opportunities/oss-contributions.mdx — complete | — | — |
| — | moved-to-about-livepeer-protocol/ — verify all redirects active, remove files | F05 | Phase 1 F05 |

B19 Gate: node tests/run-all.js --skip-browser + section freeze gate for developers section

## Phase 3 — Section Freeze & Locale Parity

After B19 gate passes, execute the full Developers section freeze as defined in SemanticUI-PLAN:

# Section freeze gates (developers section)

node tests/unit/docs-navigation.test.js --strict-missing

node tests/integration/v2-link-audit.js --full --strict \

--report tasks/reports/ungenerated/v2-link-audit-section-freeze-developers.md

node tests/run-all.js --skip-browser

# Then locale batch LB16 through LB19

node tools/scripts/i18n/translate-docs.js \

--scope-mode paths_file \

--paths-file tasks/reports/semantic-rollout/B16-files.txt \

--languages es,fr,zh-CN \

--route-map tasks/reports/i18n/LB16-route-map.json \

--dry-run

# Remaining Gaps After All Phases — Honest Assessment

Even after all three phases are complete, the following are acknowledged gaps requiring further investment:

| Gap | Risk | Owner |
| --- | --- | --- |
| WebRTC / low-latency streaming docs | Medium — growing developer interest in <1s latency | Foundation + Streamplace |
| NaaP Dashboard API key flow documentation | Medium — key developer onboarding surface, in active development | NaaP team (Qiang.Han) |
| Batch AI job documentation | Low-medium — separate from LV2V, needs dedicated page | SDK team (j0sh) |
| x402 / payment clearinghouse developer docs | Low — in design phase, not production | Future batch (B25+) |
| Browser-based gateway (BYOC) guide | Low-medium — j0sh confirmed BYOC is browser-compatible | Future content |
| Go / Java SDK parity with Python docs | Low — Go/Java SDKs exist but not documented to same level | Foundation |

# Success Criteria — Developers Section

The Developers section is production-ready when:

- A developer can get an API key, authenticate, and make their first AI inference call using the quickstart with zero additional research.

- A developer can create a stream, send RTMP, and play it back using the quickstart.

- The progression from hosted API → local SDK → self-hosted gateway is explained clearly with links to each path.

- The developer-platforms/ section accurately represents all 5 platforms (Daydream, Studio, Frameworks, Streamplace, Embody) with working external links — since the Platforms tab is gone, this is the only discovery surface.

- The Local Gateway SDK (livepeer-python-gateway) has documented working code for LV2V, BYOC, and authentication.

- All B16–B19 gates pass clean.

- Zero ⚠️ stub pages remain in the developers section visible navigation.

# Source of Truth References

| Content Area | Authoritative Source |
| --- | --- |
| Local Gateway SDK | https://github.com/j0sh/livepeer-python-gateway |
| SDK Examples | https://github.com/j0sh/livepeer-python-gateway/tree/main/examples |
| Dream Gateway AI Endpoints | https://dream-gateway.livepeer.cloud + OpenAPI spec in gateways/references/ |
| Studio REST API | https://docs.livepeer.studio/reference/api |
| BYOC / Generic Pipeline | https://github.com/livepeer/go-livepeer (BYOC issues/PRs) + Roaring30s/livepeer-byoc |
| NaaP Dashboard | https://github.com/livepeer/naap |
| Remote Signer (test) | https://signer.eliteencoder.net + EliteEncoder PR history |
| AI Worker Endpoints | https://github.com/livepeer/ai-runner |
| ComfyStream | https://github.com/livepeer/comfystream |
| Pytrickle | https://github.com/livepeer/pytrickle |
| RTMP Ingest URL | rtmp://rtmp.livepeer.studio/live (current, verified) |
| Discord — Local Gateways | #local-gateways channel — j0sh, EliteEncoder, Qiang.Han |

Plan 3: Overall Updated Plan  |  Livepeer Docs v2 Developers Section  |  March 2026  |  Aligned to SemanticUI B16–B19